## Sheet1
The Townes at Hidden Valley (Phase 1)
Issue Date on map | 12/11/2007 |  |  | 1 | Cover
Submitted to review | 05/09/2007 |  |  | 2 | ExistSite
Plan Approved | 01/31/2008 |  |  | 3 | ExistBoundary
As-Built | 12/01/2008 |  |  | 4 | Prop.Subdivision/Esmts | Keagy Rd, Towne Dr North & South, 4800-4900BlkLaryne Ln
Substantial Completion | 04/21/2010 |  |  | 14 | Plan-Overall | Keagy Rd, Towne Dr North & South, 4800-4900BlkLaryne Ln
Final Acceptance | 05/11/2010 |  |  | 15 | VOID
|  |  |  | 16 | 30' scale | Keagy Rd, Towne Dr North & South, 4800-4900BlkLaryne Ln
Street Names: | Addresses: | Utilities |  | 26 | Waterlines A, B, C | Keagy Rd, Towne Dr North & South, 4800-4900BlkLaryne Ln
Keagy Rd | 4700Blk | Waterline 'A' | Sewerline 'A' | 27 | VOID
Towne Dr South | n/a | Waterline 'B' | Sewerline 'B' | 29 | Sewerline A (Off-site) | Keagy Rd & Towne Dr South
Laryn Ln | 4800-4900Blk | Waterline 'C' | Sewerline 'C ' & Force Main | 30 | Sewerlines A, B, C, FM | Keagy Rd, Towne Dr North & South, 4800-4900BlkLaryne Ln
Towne Dr North | 4900Blk |  |  | 3 pages | Inspector Hand As-Builts | MH info and sewer laterals
The Townes at Hidden Valley (Phase 2-Partial)
Issue Date on map | 01/20/2010 |  |  | 1 | Cover
Submitted to review | 06/11/2013 |  |  | 2 | ExistSite
Plan Approved | 08/20/2013 |  |  | 3 | ExistBoundary
As-Built | 03/11/2015 |  |  | 4 | Prop.Subdivision/Esmts
Substantial Completion | 03/20/2015 |  |  | 6 | Plan-Overall-Site Phasing
Final Acceptance | 01/08/2016 |  |  | 15 | Overall-Utility | 4700BlkLarynLn-4600BlkLeighLn
|  |  |  | 17 |  | done in phase 1
|  |  |  | 27 |  | done in phase 1
|  |  |  | 28 | Waterline 'D' | 4700BlkLaryn Ln
|  |  |  | 29 | Waterline 'E' | 4600BlkLeigh Ln
|  |  |  | 30 |  | done in phase 1
Street Names: | Addresses: | Utilities |  | 32 | Sewerlines D,E | 4700BlkLaryn Ln, 4600BlkLeighLn
Laryn Ln | 4700Blk | Waterline 'D' |  | 43 | Details-Water
Leigh Ln | 4600Blk | Waterline 'E' | Sewerlines D,E | 44 | Details-Sewer
The Townes at Hidden Valley (Phase 2-Complete)
Issue Date on map | 01/20/2010 |  |  | 1 | Cover
Submitted to review | 06/11/2013 |  |  | 2 | ExistSite
Plan Approved | 09/13/2013 |  |  | 3 | ExistBoundary
As-Built | 12/11/2015 |  |  | 4 | Prop.Subdivision/Esmts
Substantial Completion | 12/11/2015 |  |  | 6 | Plan-Overall-Site Phasing
Final Acceptance | 01/08/2016 |  |  | 15 | Plan-OverallUtility
|  |  |  | 16 | 30'Scale-Utility-North | 4600-4800BlkLeighLn-4700BlkLarynLn
|  |  |  | 29 | Waterline 'E' | 4700-4800Blk Leigh Ln
|  |  |  | 32 | SewerForceMain | 4700-4800Blk Leigh Ln
|  |  |  | 43 | Details-Water
|  |  |  | 44 | Details-Sewer
Street Names: | Addresses: | Utilities
Leigh Ln | 4700-4800Blk | Waterline 'E' | Sewer Force Main
Leigh Ln waterline and sewer force main with this phase - completed all of the 3 phases